## Jira Backlog
Issue ID | Title | Description | Story Points | Assignee | Branch Name | Status
JIRA-1 | Setup Flask Project | Initialize Flask app structure | 3 | Abhishi | feature/setup-flask | To Do
JIRA-2 | Integrate NLP Model | Load Helsinki-NLP model using transformers | 5 | Abhishi | feature/nlp-integration | To Do
JIRA-3 | Create UI | Design HTML form for input/output | 3 | Abhishi | feature/ui-design | To Do
JIRA-4 | API Endpoint | Create /translate API endpoint | 4 | Abhishi | feature/api-endpoint | To Do
JIRA-5 | Error Handling | Handle empty input and model errors | 2 | Abhishi | feature/error-handling | To Do
JIRA-6 | Testing | Unit and integration testing | 5 | Abhishi | feature/testing | To Do
JIRA-7 | Deployment on Render | Deploy app using Render | 4 | Abhishi | feature/deployment | To Do
JIRA-8 | Documentation | Write README and usage guide | 2 | Abhishi | feature/docs | To Do